## Agile Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Virtual Assisstant | Bakri Kh. | 2022-07-02 | 2022-08-10 |  | 70% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 - App Design and Database |  | Bakri Kh. |  | 2020-07-03 | 2020-07-13 | 10 | Complete
| UI/UX Design |  | Muhammed Kh. |  | 2020-07-03 | 2020-07-10 | 7 | Complete
| Database Schema Building |  | Bakri Kh. |  | 2020-07-07 | 2020-07-10 | 3 | Complete
| Sprint 2 - Voice Input Features |  | Muhammed Kh. |  | 2020-07-16 | 2020-07-24 | 8 | Complete
| Voice Input Feature |  | Bakri Kh. |  | 2020-07-16 | 2020-07-17 | 1 | Complete
| Keyword Recognition |  | Muhammed Kh. |  | 2020-07-17 | 2020-07-21 | 4 | Complete
| Voice Commands Recognition |  | Muhammed Kh. |  | 2020-07-22 | 2020-07-24 | 2 | Complete
| Sprint 3 - API And Data Filling |  | Bakri Kh. |  | 2020-07-25 | 2020-08-05 | 11 | In Progress
| Fill The Database |  | Muhammed Kh. |  | 2020-07-25 | 2020-07-27 | 2 | In Progress
| API Development |  | Bakri Kh. |  | 2020-07-24 | 2020-08-02 | 9 | In Progress

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.